## Sheet1
Workflow 1
Workflow 2
Combined
Michaelmas
Tasks | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Research and familiarisation with OptiTrack
Stream live data and render markers rigid bodies
Debug rendering
Return live labelled rigid bodies with position and rotation.
Design pilot experiment task
Write 2D simulated task interface with PID control and 1D mouse input
Generalise to 3D simulation with 2D mouse input and update/debug interface
Integrate simulated task interface with live optitrack data
Conduct pilot experiment (with us as subjects)
Buffer week + Individualise project aims
Project plan, timeline, grant proposal
Lent
Tasks | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Collect data from real participants
Individual project plans (TBD)